## Sheet1
Component | Functional Purpose | Failure Mode* | Failure Effect | Failure Cause | Current Situation |  |  |  | Assigned Action | Improved Situation
[5 empty] | S | L | D | RPN |  | S | L | D | RPN
RC Reciver | Communicate Manual Commands from the RC Transmittor to F4 | Hardware Failure* | Mission Failure Aircraft Loiters | Poorly Connected Electrical Joint | 8 | 1 | 7 | 56 |  | 8 | 1 | 7 | 56
|  | Transmits incorrect data | Crash | Internal Code | 9 | 1 | 10 | 90 | Extensive testing prior to use** | 9 | 1 | 10 | 90
|  | Loss of Connection | Mission Failure Aircraft Loiters | Interference | 8 | 4 | 9 | 288 | FFCL*** range test | 8 | 4 | 3 | 96
RC Transmittor | Communicate Commands from the RC Pilot to the RC Reciver | Hardware Failure | Mission Failure Aircraft Loiters | Poorly Connected Electrical Joint | 8 | 2 | 7 | 112 | FFCL | 8 | 2 | 3 | 48
|  | Transmits incorrect data | Crash | Settings Incorrect | 9 | 2 | 6 | 108 | FFCL | 9 | 1 | 4 | 36
|  | Loss of Connection | Mission Failure Aircraft Loiters | Settings Incorrect | 8 | 6 | 8 | 384 | FFCL | 8 | 4 | 3 | 96
|  |  |  | Interference | 8 | 4 | 9 | 288 | FFCL, and laboratory debugging | 8 | 6 | 3 | 144
|  |  |  | Transmittor Battery Dead | 8 | 6 | 3 | 144 | FFCL | 8 | 4 | 2 | 64
WIFI antenna | Allow communitation with grounstation over ROS network | Hardware Failure | Mission Failure Manual Landing | Poorly Connected Electrical Joint | 6 | 1 | 7 | 42 |  | 6 | 1 | 7 | 42
|  | Loss of Connection | Mission Failure Manual Landing | Antenna Incorrectly Pointed | 6 | 7 | 3 | 126 | Assign someone to point antenna | 6 | 3 | 3 | 54
Odroid | Run ROS, generate high level commands, process images, & estimate state | Hardware failure | Mission Failure Manual Landing | Poorly Connected Electrical Joint | 6 | 2 | 7 | 84 |  | 6 | 2 | 7 | 84
|  |  | Crash | Poorly Connected Electrical Joint | 9 | 1 | 7 | 63 | Extensive testing prior to use | 9 | 1 | 3 | 27
F4 Flight Computer & Mount | Turn high level (Odroid & RC) commands into low level servo commands | Software Failure | Crash | Internal Code | 9 | 3 | 6 | 162 | Extensive testing prior to use | 9 | 3 | 3 | 81
|  | Hardware Failure | Crash | Poorly Connected Electrical Joint | 9 | 3 | 7 | 189 | Extensive testing prior to use | 9 | 3 | 3 | 81
Airspeed Sensor | Measure Va | Software Failure | Flight Less Smooth | Internal Code | 4 | 1 | 10 | 40 |  | 4 | 1 | 10 | 40
|  | Inaccurate Readings | Flight Less Smooth | Plugged Pito Tube | 4 | 4 | 5 | 80 |  | 4 | 4 | 5 | 80
|  |  |  | High Angle of Attack | 4 | 4 | 2 | 32 |  | 4 | 4 | 2 | 32
|  |  |  | Incorrect Mounting | 4 | 2 | 2 | 16 |  | 4 | 2 | 2 | 16
|  | Hardware Failure | Flight Less Smooth | Poorly Connected Electrical Joint | 4 | 1 | 7 | 28 |  | 4 | 1 | 7 | 28
Inertial Sense | Measure acceleration, barometter data, and magnetic heading | Software Failure | Crash | Internal Code | 9 | 1 | 10 | 90 | Extensive testing prior to use | 9 | 1 | 3 | 27
|  | Inaccurate Readings | Crash | Interference | 9 | 3 | 8 | 216 | Extensive testing prior to use | 9 | 3 | 3 | 81
|  | Hardware Failure | Crash | Poorly Connected Electrical Joint | 9 | 1 | 7 | 63 | Extensive testing prior to use | 9 | 1 | 3 | 27
GPS | Measure global position | Software Failure | Crash | Internal Code | 9 | 3 | 10 | 270 | Extensive testing prior to use | 9 | 3 | 3 | 81
|  | Inaccurate Readings | Crash | Interference | 9 | 4 | 5 | 180 | FFCL | 9 | 2 | 4 | 72
|  | Hardware Failure | Mission Failure Manual Landing | Poorly Connected Electrical Joint | 6 | 1 | 7 | 42 |  | 6 | 1 | 7 | 42
Battery | Provide current to all systems in the air | Loss of Power | Crash | Battery Not Charged Correctly | 9 | 5 | 3 | 135 | FFCL | 9 | 5 | 2 | 90
|  |  |  | Chemical Misshap | 10 | 2 | 3 | 60 | Assign battery saftey officer | 10 | 1 | 2 | 20
|  |  |  | Battery Degridation | 9 | 1 | 1 | 9 | FFCL | 9 | 1 | 1 | 9
ESCs | BEC and convert digital logic PWM to high voltage/current motor inputs | Hardware Failure | Crash | Poorly Connected Electrical Joint | 9 | 1 | 7 | 63 | Extensive testing prior to use | 9 | 1 | 3 | 27
Motors | Rotate Props | Overheat | Fire and Crash | Overstressing the Motors | 10 | 3 | 5 | 150 | Add warning to FFCL | 10 | 2 | 5 | 100
|  | Does Not Transmit Tourque | Mission Failure Glide to Safe Landing | Props Unsecured | 7 | 8 | 3 | 168 | FFCL | 7 | 5 | 2 | 70
|  | Rotates the Wrong Way | Mission Does Not Start | Wires Connected Backwards | 6 | 3 | 2 | 36 | FFCL | 6 | 1 | 2 | 12
|  | Hardware Failure | Mission Failure Glide to Safe Landing | Poorly Connected Electrical Joint | 7 | 1 | 7 | 49 |  | 7 | 1 | 7 | 49
Props | Provide Thrust | Does Not Provide Thrust | Mission Failure Glide to Safe Landing | Chipped/broken prop | 7 | 5 | 3 | 105 |  | 7 | 5 | 3 | 105
Wiring | Transmit power and signals | Provides Electricty to Incorrect Location | Crash | Wires Connected to Incorrect Ports | 9 | 7 | 8 | 504 | FFCL | 9 | 3 | 3 | 81
|  | Does Not Transmit Electricity | Crash | Electrical Short Circuit | 9 | 3 | 8 | 216 | Shrink wrap all exposed wires | 9 | 1 | 8 | 72
|  |  | Crash | Electrical Open Circuit | 9 | 8 | 5 | 360 | FFCL | 9 | 8 | 1 | 72
Servos | Move control surfaces | Linkage Breaks | Crash | Poorly Assembled | 9 | 2 | 7 | 126 | Extensive testing prior to use | 9 | 2 | 5 | 90
|  |  |  | Large Controll Inputs at High Velocity | 9 | 1 | 3 | 27 | Train saftey pilot | 9 | 1 | 3 | 27
|  | Mechanical Limits Exceeded | Crash | Aerobatic Flight Saturates Controller | 9 | 5 | 8 | 360 | Train saftey pilot | 9 | 1 | 4 | 36
|  |  |  | Poorly Assembled | 9 | 6 | 4 | 216 | Extensive testing prior to use | 9 | 2 | 4 | 72
|  | Software Failure | Crash | Internal Code | 9 | 1 | 10 | 90 | Extensive testing prior to use | 9 | 1 | 3 | 27
|  | Hardware Failure | Crash | Poorly Connected Electrical Joint | 9 | 1 | 7 | 63 | Extensive testing prior to use | 9 | 1 | 3 | 27
|  | Internal Mechanics Broken | Crash | Overuse | 9 | 2 | 5 | 90 |  | 9 | 2 | 5 | 90
|  | Servo Burns Out | Crash | Overuse | 9 | 2 | 5 | 90 |  | 9 | 2 | 5 | 90
UGV System | Deliver water bottle to both ground locations | See UGV Documentation for UGV FMEA
Imaging System | Capture, interperate, and report ground targets | See Imaging Documentation for Imaging FMEA
Control Software | Pilot aircraft autonomusly | See Control Documentation for Control FMEA
Communication Software | Allow communication of all components | See Communication Documentation for Communication FMEA
Airframe Body | Contain components, provide lift, provide stability, & respond to control inputs | Flight Characteristics Change | Crash | Icing | 9 | 2 | 1 | 18 | Only fly in good weather | 9 | 1 | 1 | 9
|  |  |  | Components Move | 9 | 5 | 5 | 225 | Strap down all components | 9 | 3 | 3 | 81
|  | Parts Break Off | Crash | Flight Envelop Exceeded | 9 | 2 | 3 | 54 | Train saftey pilot | 9 | 2 | 2 | 36
|  |  |  | Poor Manufacturing | 9 | 6 | 7 | 378 | Extensive testing prior to use | 9 | 6 | 2 | 108
|  |  |  | Part poorly attached | 9 | 2 | 7 | 126 | FFCL | 9 | 2 | 3 | 54
|  |  |  | Unidentified Flying Object (UFO) Impact | 9 | 1 | 3 | 27 | Train saftey pilot | 9 | 1 | 3 | 27
Ground stations | Transmit high level commands between operators and WIFI router | Battery Dies | Mission Failure Manual Landing | Charger Not Connected | 6 | 1 | 1 | 6 |  | 6 | 1 | 1 | 6
|  | Hardware Failure | Mission Failure Manual Landing | Poorly Connected Electrical Joint | 6 | 1 | 7 | 42 |  | 6 | 1 | 7 | 42
|  | Software Failure | Crash | Bug in Code | 9 | 7 | 10 | 630 | Extensive testing prior to use | 9 | 4 | 3 | 108
WIFI Router | Trasmit data over ROS network between groundstations to light beam | Loss of Connection | Mission Failure Manual Landing | Interference | 6 | 2 | 7 | 84 |  | 6 | 2 | 7 | 84
|  | Hardware Failure | Mission Failure Manual Landing | Poorly Connected Electrical Joint | 6 | 1 | 7 | 42 |  | 6 | 1 | 7 | 42
|  | Software Failure | Mission Failure Manual Landing | Internal Code | 6 | 1 | 10 | 60 |  | 6 | 1 | 10 | 60
WIFI Light Beam | Transmit data over ROS network between WIFI router and the WIFI antenna on the aircraft | Loss of Connection | Mission Failure Manual Landing | Interference | 6 | 8 | 7 | 336 | Laboratory debugging | 6 | 5 | 7 | 210
|  | Hardware Failure | Mission Failure Manual Landing | Poorly Connected Electrical Joint | 6 | 1 | 7 | 42 |  | 6 | 1 | 7 | 42
|  | Software Failure | Mission Failure Manual Landing | Internal Code | 6 | 1 | 10 | 60 |  | 6 | 1 | 10 | 60
Ground Power Source | Provide current to all ground systems | Not Brought with Us | Mission Does Not Start | Poor Planning | 4 | 8 | 4 | 128 | FFCL | 4 | 4 | 4 | 64
|  | Mechanical Failure | Mission Failure Manual Landing | Poor Manufacturing | 6 | 1 | 7 | 42 |  | 6 | 1 | 7 | 42
Human Operators | Give high level commands & ensure saftey of flight | Sick | Mission Does Not Start | Bacteria or Viruses | 5 | 4 | 3 | 60 |  | 5 | 4 | 3 | 60
|  | Can Not Attend | Mission Does Not Start | Other Plans | 5 | 1 | 1 | 5 |  | 5 | 1 | 1 | 5
|  | Sends Incorrect Commands | Crash | Poor Judgement | 9 | 2 | 9 | 162 | Extensive practice | 9 | 1 | 9 | 81
|  |  | Crash | Poor Understanding of System | 9 | 2 | 5 | 90 | Extensive practice | 9 | 1 | 5 | 45
|  | * In this analysis "Hardware Failure" refers only to electrical hardware (e.g. USB port breaks or soldering fails) |  |  | S: Severity of failure effect
|  | ** FFCL is the Field Flight Checklist to which we will add items to test and do before flight |  |  |  | L: Likelihood of failure occurring
|  | *** Extensive testing before use refers to extensive flight tests before the competition. |  |  |  |  | D: Dectability of cause before failure occurs
|  |  | We currently perform flight tests a couple times a week. |  |  |  |  | RPN: Risk Priority number (S*L*D)